**change log**

**dynamic developers**

**4601 Mid Rivers Mall Drive**

**cottleville, mo 63376**

**7/24/2020**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Change Log** | | | | | | | |
| **Project: Car-Nerd** | | | | | | **Date: 7/25/2020** | |
| **Change No.** | **Change Type** | **Description of Change** | **Requestor** | **Date Submitted** | **Date Approved** | **Status** | **Comments** |
| RC01 | Scope | This change request removed Tier 2 from the application as it was determined there were too many features for the scope of this project. | Professor Wang | 6/13/2020 | 6/15/2020 | Approved | Request was approved to ensure there would be enough time for the team to complete all phases of the project. |
| RC02 | Scope/ Design | This change request removed the Documents tab from the UI design and merged Log and Reminders into one tab. | Kelli | 6/25/2020 | 6/25/2020 | Approved | Request was approved due to time and resource constraints for completing those tasks. |
| RC03 | Design | This change request updated the existing system architecture document. | Professor Wang | 6/27/2020 | N/A | Deferred | This request has been deferred and is pending until requestor has finished reviewing this document. |
| RC04 | Design | This change request implemented a main window design as opposed to the multiple tab design originally proposed. | Development Team | 6/28/2020 | 6/28/2020 | Approved | Request was approved as the development team deemed that a main window approach would provide users with a better overall experience. |
| RC05 | Design | This requested change updates the existing UI design due to the decision to change from a multiple tab design to a main window design. | Development Team | 6/30/2020 | 6/30/2020 | Approved | This request was approved in order to keep all design components aligned. |
| RC06 | Design | Moved from using JPane frames to using dialog boxes for pop up windows. | Development Team | 7/14/2020 | 7/14/2020 | Approved | This was approved as the JPane frames were causing many code issues for the development team. |
| RC07 | Other | This request change reorganizes the team’s existing GitHub repository. | Alyssa/William | 7/19/2020 | 7/21/2020 | Approved | This was approved due to the repository being easier to read and assisting with keeping track of code changes. |